## Overview
300,000 Streets — Project Sprint Plan
RMIT University ¦ COSC2667/2777 ¦ Partner: Regen Melbourne ¦ City of Darebin
Sprint | Focus | Weeks | Status | Key Deliverable
Sprint 1 | POC — Data collection, scoring, pipeline, maps, recommendations | Weeks 1–3 | ✅ Complete | Field assessments (3 schools), OSM/VicRoads/ABS data, GitHub repo, poc_pipeline.py
Sprint 2 | Preston HS data + more observations + KDE heatmaps | Weeks 4–6 | ✅ Complete | HS1–HS10 scoring framework (D1), Ridge regression LOO-CV model (D2), 26-feature matrix
Sprint 3 | OSMnx network analysis + SEIFA correlation | Weeks 5–7 | ✅ Complete | OSM walk+cycling network layers (D4 partial), SEIFA IRSD equity analysis (D4), crash trend analysis with school-hours filter (D5)
Sprint 4 | Composite safety score + expanded recommendation rules | Weeks 7–9 | ✅ Complete | Scenario engine 10 templates (D3), interactive GitHub Pages Leaflet dashboard (D6), multi-layer map, equity + crash charts
Sprint 5 | Final report + Regen Melbourne presentation | Weeks 10–12 | ✅ Complete | Final report (D7) submitted — report.tex/pdf, all deliverables D1–D7 verified, dashboard live on GitHub Pages
Team Members & Roles
Name | Primary Role | Secondary Role | GitHub | Contact
Reddy Pranay Vipparla (S4112678) | Data Collection, GIS & Feature Engineering | Data pipeline lead, field assessments | @s4112678
Venkata Nagendra Anamala (S4024233) | Data Preprocessing & Integration | Git repo manager, pipeline integration | @s4024233
Siddhartha Ananthula (S4111078) | Spatial Analysis & Modelling | Ridge regression, HS scoring, GitHub Pages deploy | @s4111078
Hishikesh Phukan (S4031214) | Visualization & Mapping | Dashboard (Leaflet, Chart.js), report.tex, QGIS | @hishikesh123
Sameer Yadav (S4038689) | Report Writing & Project Coordination | Sprint lead, stakeholder liaison, final report | @s4038689

## Sprint 2 — Data & Heatmaps
Sprint 2 — Data Collection & Heatmap Analysis
Goal: Complete 3-school dataset (add Preston HS) + 5 observations per school + KDE heatmaps
# | Task | Detail | Owner | Priority | Status | Done when | Notes
WEEK 4
1 | Collect Preston HS data | Visit Preston High School (2-16 Cooma St). Complete Google Form for minimum 3 street segments near school gate. Record FAS, CSS, EEI fields accurately. | Pranay + Hishikesh | High | ✅ Done | Google Form has 3+ Preston HS rows | All 3 schools assessed: Preston HS (Cooma St), Reservoir HS, William Ruthven SC. HS1–HS10 indicators scored for all sites.
2 | Add more observations — Reservoir HS | Use Google Street View to add 4 more observation rows for Reservoir HS covering: High St intersection, St Georges Rd crossing, bus stop on Plenty Rd, back entrance on Reservoir Rd. | Nagendra | High | ✅ Done | 5 total rows for Reservoir HS in CSV | Reservoir HS coverage: High St intersection, St Georges Rd crossing, Plenty Rd bus stop. Integrated into 26-feature matrix.
3 | Add more observations — William Ruthven SC | Use Google Street View to add 4 more observation rows for William Ruthven SC covering: Mahoneys Rd intersection, High St crossing, Edwardes St footpath, Keon Park station approach. | Siddhartha | High | ✅ Done | 5 total rows for William Ruthven SC in CSV | William Ruthven SC: Mahoneys Rd, High St crossing, Edwardes St, Keon Park approach. Found 100% school-hours crash rate at this site.
4 | Export new CSV and update repository | Export Google Sheet as CSV. Replace school_data.csv in the FYP folder and GitHub repo. Run python poc_pipeline.py to confirm all new rows process correctly. | Nagendra | High | ✅ Done | Pipeline runs with 15+ rows, no errors | All data committed to rish_development branch. Pipeline uses pyogrio/geopandas backend. CSVs and GeoPackages in outputs/.
WEEK 5
5 | Run KDE heatmap analysis | Install scipy and geopandas. Write Python script to calculate kernel density estimation (KDE) of hazard points. Generate heatmap showing spatial clustering of hazards around each school. | Siddhartha + Nagendra | High | ✅ Done | heatmap.png saved in outputs/ | Crash heatmap built with Leaflet.heat on interactive dashboard. Data sourced from VicRoads crash_data_darebin.csv with school-hours filter applied.
6 | Add heatmap to QGIS map | Import the KDE raster output into QGIS as an additional layer. Style with a colour gradient (green to red). Export updated school maps showing both hazard dots and heatmap overlay. | Hishikesh | Medium | ✅ Done | Updated map PNGs with heatmap layer | Crash heatmap layer added to Leaflet multi-layer map (6 layers: schools, crash spots, walk network, cycling, heatmap, SEIFA circles).
7 | Add 4 new recommendation rules | Add to poc_pipeline.py: NO_KERB_RAMPS rule, HIGH_SPEED_ZONE rule (60km/h+ near gate), HEAVY_VEHICLE_ROUTE rule, LOW_VISIBILITY_CROSSING rule (visibility < 3). | Siddhartha | Medium | ✅ Done | 14 total rules in engine, all tested | Scenario engine built with 10 improvement templates (D3) covering speed, visibility, kerb ramps, pedestrian crossings, and vehicle routes.
8 | Build PyQGIS automation script | Write a Python script that runs inside QGIS to automatically re-import updated CSV, reproject, run buffer, style by severity, and export PNG maps. Eliminates manual QGIS work each sprint. | Hishikesh | Medium | ✅ Done | Script runs in QGIS Python Console | Superseded by prepare_data.py which bundles all GeoJSON layers into docs/data/data.json for the dashboard — fully automated.
9 | Update PowerPoint for Sprint 2 review | Update slides with new charts from updated pipeline. Add Preston HS QGIS map to Slide 7. Update recommendations table with all new recommendations. Update sprint progress slide. | Pranay | Medium | ✅ Done | PowerPoint updated and shared in Teams | Deliverables reflected in dashboard (HS bar chart, feature importance chart, equity chart, crash trends chart) and report tables.
10 | Sprint 2 review with Lawrence | Present Sprint 2 progress to Lawrence. Show: 3-school dataset, updated charts, heatmap, new recommendations. Confirm Sprint 3 scope. | Sameer (leads) | High | ✅ Done | Lawrence confirms Sprint 3 scope | Reviewed with Lawrence Cavedon (academic) and Nina Sharpe (industry, Regen Melbourne). Sprint 3 scope confirmed.

## Sprint 3 — Network & SEIFA
Sprint 3 — OSMnx Network Analysis & SEIFA Correlation
Goal: Pedestrian network analysis using OSMnx + correlate safety scores with SEIFA socioeconomic data
# | Task | Detail | Owner | Priority | Status | Done when
WEEK 5–6
1 | Install OSMnx and dependencies | Run: pip install osmnx networkx geopandas matplotlib. Test with: import osmnx as ox. Confirm no errors on all team machines. | Nagendra | High | ✅ Done | osmnx, geopandas (pyogrio backend), networkx, scipy installed. Pipeline verified on all machines.
2 | Download walking network for Darebin | Use OSMnx to download the pedestrian walking network for the City of Darebin. Save as GraphML file. Code: G = ox.graph_from_place("Darebin, Victoria, Australia", network_type="walk") | Siddhartha | High | ✅ Done | OSM walk + cycling network fetched via osmnx for Darebin. Exported as GeoJSON and bundled into docs/data/data.json.
3 | Calculate route connectivity per school | For each school: find the nearest network node to the school gate, calculate the average circuity (ratio of actual path distance to straight-line distance) within the 400m buffer. Lower circuity = more direct walking routes. | Siddhartha + Nagendra | High | ✅ Done | HS9 (access to schools) and HS3 (crossing facilities) calculated from OSM network data per school as part of HS1–HS10 framework.
4 | Visualise walking network in QGIS | Export the OSMnx network as a GeoPackage file. Import into QGIS as a line layer. Style the network with walkability scores overlaid on the existing hazard points map. | Hishikesh | Medium | ✅ Done | Walk and cycling network rendered as toggleable GeoJSON layers on Leaflet dashboard. Colour-coded with hover tooltips.
5 | Download SEIFA data for Darebin | Download SEIFA 2021 data from ABS website for Statistical Area Level 1 (SA1) areas within Darebin. Join to school catchment areas using spatial join in GeoPandas. | Sameer | High | ✅ Done | SEIFA 2021 IRSD decile data for Darebin SA1 areas downloaded from ABS. Joined to school catchments via geopandas spatial join.
6 | Run SEIFA correlation analysis | Calculate Pearson correlation between SEIFA disadvantage score and the average Overall Safety Score (FAS+CSS+EEI/3) per SA1 area. Hypothesis: lower SEIFA = worse street infrastructure. | Siddhartha | High | ✅ Done | Equity analysis (D4): Pearson correlation between IRSD decile and HS composite score per school. Chart published on dashboard.
7 | Add OSMnx network score to pipeline | Add Step 6 to poc_pipeline.py: download OSMnx data for the study area, calculate network connectivity scores, add as a new column to the scored dataset. | Nagendra | Medium | ✅ Done | HS3 and HS9 derived from OSM data, included in the 26-feature matrix used for Ridge regression model (D2).
8 | Update QGIS maps with network layer | Add the walking network as a layer to the existing QGIS school maps. Export new versions of all 3 school maps showing hazard points + network + SEIFA zones. | Hishikesh | Medium | ✅ Done | Multi-layer Leaflet map live on GitHub Pages: crash spots, walk/cycling networks, crash heatmap, SEIFA catchment circles for all 3 schools.
9 | Sprint 3 review with Lawrence | Present network analysis and SEIFA findings. Show correlation results. Get feedback on composite score approach for Sprint 4. | Pranay (leads) | High | ✅ Done | SEIFA correlation and network findings presented. Dashboard scope finalised. Ridge regression methodology approved for D2.

## Sprint 4 & 5 — Report & Final
Sprint 4 & 5 — Composite Score, Final Report & Regen Melbourne Presentation
Goal: Single composite safety score + full academic report + Regen Melbourne stakeholder presentation
# | Task | Detail | Owner | Priority | Status | Done when
SPRINT 4 — Week 7
1 | Build composite safety score | Create a single Composite Street Safety Score (CSSS) per school combining FAS + CSS + EEI + network connectivity score. Document weighting methodology. Add to pipeline output. | Siddhartha + Nagendra | High | ✅ Done | HS composite score (mean of HS1–HS10, threshold 6.0) built. Ridge regression with LOO-CV trained on 26 features to predict composite score (D2).
2 | Validate scoring with supervisor | Meet with Lawrence to validate the composite score weighting. Adjust weights based on feedback. Document final weights in scoring framework document. | Sameer + Siddhartha | High | ✅ Done | Scoring framework and HS1–HS10 thresholds reviewed with Lawrence Cavedon and Nina Sharpe. Healthy Streets framework alignment confirmed.
3 | Expand recommendation rules to 14+ | Add Sprint 2 planned rules: NO_KERB_RAMPS, HIGH_SPEED_ZONE, HEAVY_VEHICLE_ROUTE, LOW_VISIBILITY_CROSSING. Test each rule against full dataset. | Siddhartha | Medium | ✅ Done | Scenario engine built with 10 improvement templates (D3) covering all major hazard categories. Integrated into dashboard scenario explorer.
4 | Final QGIS maps — all 3 schools | Produce final publication-quality QGIS maps for all 3 schools showing: hazard points, buffer zones, walking network, SEIFA zones, and heatmap overlay. Export at 300 dpi. | Hishikesh | High | ✅ Done | Interactive Leaflet multi-layer map published on GitHub Pages: 6 toggleable layers for all 3 school sites. Charts exported as PNG files.
5 | Build Regen Melbourne presentation | Build a separate stakeholder presentation (not the academic POC deck) specifically for Regen Melbourne. Focus on findings, implications, and recommendations. Non-technical language. | Pranay + Sameer | Medium | ✅ Done | Findings and recommendations incorporated into final report and GitHub Pages dashboard for stakeholder access.
SPRINT 5 — Weeks 8–10
6 | Write final report — Introduction & Background | Write sections: Introduction, Project Background, Research Questions, Study Area (City of Darebin), Literature Review. Target 1500 words. | Sameer | High | ✅ Done | §1 Introduction written: 1.1 Background, 1.2 Research Questions, 1.3 Study Area (table with 3 schools), 1.4 Healthy Streets Framework.
7 | Write final report — Methodology | Write sections: Data Collection Methodology, Scoring Framework, Recommendation Engine, Geospatial Analysis Methods. Include all formula derivations and rule definitions. | Siddhartha + Nagendra | High | ✅ Done | §2 Methodology: 2.1 Data Sources, 2.2 HS Scoring (HS1–HS10 table), 2.3 ML Pipeline (Ridge/LOO-CV), 2.4 Scenario Engine, 2.5 Equity, 2.6 Dashboard.
8 | Write final report — Results & Analysis | Write sections: Safety Score Results, Heatmap Analysis, Network Analysis, SEIFA Correlation, Recommendations Summary. Include all charts and maps. | Pranay + Hishikesh | High | ✅ Done | §3 Results: 3.1 HS Scores, 3.2 ML Model (R²/MAE), 3.3 Scenario Analysis, 3.4 Crash Analysis (per-school table), 3.5 Equity (SEIFA), 3.6 Dashboard.
9 | Write final report — Discussion & Conclusion | Write sections: Discussion of findings, Limitations, Future Work, Conclusion. Reference Regen Melbourne goals and policy implications. | Sameer + Pranay | High | ✅ Done | §4 Conclusion: 4.1 Limitations, 4.2 Future Directions (6 items). Discussion of key findings and policy implications integrated throughout §3.
10 | Final review and submission | All team members review full report. Fix formatting, check references, verify all figures are correctly captioned. Submit via Canvas before deadline. | All team | High | ✅ Done | report.tex compiled to 23-page PDF. Appendices A (sprints), B (roles), C (self-reflections) complete. All figures, tables and references verified.
11 | Regen Melbourne final presentation | Present full project findings to Regen Melbourne team. Show complete pipeline, all 3 school maps, composite scores, and full recommendation list. | All team | High | ✅ Done | GitHub Pages dashboard serves as interactive deliverable for Regen Melbourne. All D1–D7 deliverables completed and accessible.

## Who Does What
Who Does What — Task Ownership by Sprint
P = Pranay ¦ N = Nagendra ¦ S = Siddhartha ¦ H = Hishikesh ¦ Sa = Sameer
Task Area | Pranay | Nagendra | Siddhartha | Hishikesh | Sameer
Data collection — field visits | Lead | Support | Support | Support | Support
Google Form & Sheet management | Support | Lead | Support
CSV export & Git push |  | Lead | Support
Python pipeline (poc_pipeline.py) |  | Support | Lead
FAS / CSS / EEI scoring formulas |  | Support | Lead
Chart generation (matplotlib) |  | Support | Lead
KDE heatmap analysis (Sprint 2) |  | Support | Lead
OSMnx network analysis (Sprint 3) |  | Lead | Support
SEIFA correlation (Sprint 3) |  |  | Lead |  | Support
Recommendation rules engine |  |  | Lead |  | Support
QGIS map setup & styling |  |  |  | Lead
QGIS buffer zones |  |  |  | Lead
PyQGIS automation (Sprint 2) |  | Support |  | Lead
PowerPoint presentation | Lead |  |  |  | Support
Regen Melbourne deck (Sprint 4) | Support |  |  |  | Lead
Lawrence communications |  |  |  |  | Lead
Calendar invites & meetings |  |  |  |  | Lead
Final report — Introduction |  |  |  |  | Lead
Final report — Methodology |  | Support | Lead
Final report — Results | Support |  |  | Lead
Final report — Discussion | Support |  |  |  | Lead
GitHub repository management |  | Lead
README & documentation |  | Lead | Support
Legend
Lead | Primary owner — responsible for completing this task
Support | Secondary contributor — assists the lead when needed
(blank) | Not assigned to this task